## Read Me First
Tarpon Health IT Readiness Toolkit
Intended use
The intent of the IT Readiness Toolkit is to guide automation programs and IT departments through automation infrastructure requirements and best-practices.
Instructions
1. Users should complete the toolkit in this order: Read through the IT Checklist, select Yes or No in the "IT Follows Recommendation" boxes, view your IT readiness score/suggestion at the bottom Note: The toolkit has standard calculations and formulas created by the Tarpon Team. Please reach out if you need any clarifications.

## IT Checklist
Tarpon Health IT Readiness Toolkit
IT Checklist
Category | Decision | Recommendation | Impact If Not Followed | IT Audit/Compliance | Status | Implementation Notes
Machine | Number and type of machines | Development: 1 machine per developer (+1-2 based on upcoming builds, hires) Test: 1 test machine Production: Depends on number of robots purchased and anticipated utilization. For example, 5 unattended robots would require 5 machines if all 24 hours of bot time are utilized. Tarpon recommends starting with a portion of the required production machines (e.g. 3-4) knowing you will scale the number of production machines as the program grows | Lack of development machines will result in a lack of development capacity. A lack of production machines can result in a lack of production output if there are scheduling conflicts (e.g. 2 automations are required by operations to run at the same time of day). A lack of testing machines can result in a lack of development output if the development resource and test resource share a machine (e.g. development is haulted to run a test). | Machines will only be accessed by service credentials created by IT. Tarpon strongly encourages designated machines for running unattended production automations. An automation running on an employee's machine is a security risk due to access/privileges. | Not Started
| Machine Creation/Replication | Create a scalable template across varying levels of access Each machine needs an automation platform browser extension (e.g. UiPath Studio Chrome Extension) and browser authenticator extension (Google Authenticator) downloaded | Differences in machines between Development and Production will require additional development once the automation is transferred to the new environment. This can cause go-live delays and potentially lead to an increase in maintenance long-term. | One consistent template across multiple machines allows for a standardization resulting in less maintenance and variability in requests from IT resources. Identical machines except for application access (e.g. Epic SUP/REL/PRD). | Not Started
| Server allocation | Machines are assigned a dedicated server instead of a dynamic server allocation. | Dynamic allocation provides the automation with a new IP address upon each log in, which is recognized as a new log in location, ultimately prompting stricter MFA requirements each time the automation logs in. | Based on current compliance guidelines, dynamic allocation may be required. If required, RPA team will need to develop around it and requires additional assistance from IT for other methods of verification. | Not Started
| Virtual vs Physical (Cloud vs. On-prem) | Virtual | On-premise machines are more prone to external factors - power surges, restarts, relocation, etc. | Security measures should be in place within the server that is spinning up the virtual machines. If the machines need to be on-prem to align with current infrustructure, be aware of the potential issues. | Not Started
| Resolution | 1920 x 1080 | Automations using Computer Vision (CV) will be greatly impacted if dev and prod machine resolutions differ. Since CV uses pixel coordinates for screen capturing, a resolution difference would lead to automation instability. | Template creation/replication will allow for the same resolution across all machines | Not Started
| Hardware | CPU: 4 x 2.4GHz 64-bit (x64) RAM: 8 GB | Decreased performance |  | Not Started
| Drive access | Access to local, organization-specific drives for data (e.g. C Drive) | The majority of automation use cases require a queue of records/accounts to action, and the popular method of obtaining the queue is by export and SFTP. These are exported and placed on shared drives for the automation to reference. Without the data preloaded and placed on the shared drive, the ownership of exporting data is placed on the automation and will reduce its efficiency/output. | IT can restrict access to certain drives, folders, files to only allow access to pathways that the automation needs to reference. | Not Started
Application | Locally installed (thick client) vs Citrix apps | Locally installed clients are preferred (essentially required) for efficient automations | Citrix (without a Citrix runtime) will require use of Computer Vision within the build, which is less stable and requires more maintenance. Platforms work best when they can access native selectors within the application. | Providing a locally installed client may require additional assistance from IT in regards to version control. Depending on machine set up, if they are not included in routine upgrades it may require a manual upgrade when available. | Not Started
| Development/test environment | Automation platform, automation-associated apps (e.g. UiPath Assistant), test application environments (e.g. Epic SUP/Epic REL), ability to use browser extensions (e.g. Google Auth) | Inability to develop Data is needed in order to build/test the automation (ideally a copy of production data) | Developer has restricted access to only what is needed via machine template methodology, easy to track, production applications are not available | Not Started
| Production environment | Automation platform, automation-associated apps (e.g. UiPath Assistant), Production application environments (e.g. Epic PRD), ability to use browser extensions (e.g. Google Auth) | Inability to test a scheduled process once development is complete and/or go live | Developer has restricted access to only what is needed via machine template methodology, easy to track | Not Started
Credentialing | Whitelist websites | Automation-specific: dev and prod machines need access to certain sites for build. Browsers may be downloaded on the machine but websites leveraged will need to be whitelisted. | Inability to develop due to websites being inaccessible | Whitelisting will be integrated into the machine templates | Not Started
| SQL access | Access for writing queries regarding queueing (if data is obtainable via SQL instead of EMR/application export) Logging outputs back to a SQL table that would support PowerBI/analytics platforms | Potential for delays due to lack of data or inability to insert data for analytics. If export jobs fail, IT tickets are required for resolution. If operational data changes, RPA will need to submit change requests instead of making the change directly in the query. | Access is only for specific environments and tables. No creation/deletion of tables should be needed. | Not Started
| Dev and Service accounts | Development: Each developer should have their own credentials for accessing machines Service: Each automation should have its own credential for its intended function | Lack of credentials can lead to bottlenecks in development, production runs - this can lead to delays across the board | Active Directory (AD) groups make the accounts more secure. Each account should be in an AD group depending on what applications they need access to. Activity can be tracked across all machines based on credential. Use current naming convention for usernames or implement an automation naming convention like Account Type_Department Name_Environment_Number (e.g. SRV_PatientAccess_PRD_1) | Not Started
| Remote Login access | Developer and Service credentials are set up for remote login access | Developers/automations cannot access their machines |  | Not Started
| Application(s) | Development/Production: Each developer AND automation should have their own credentials for each application used in the automation (e.g. Availity, Epic, etc.) | Difficult to track activity and inability to map roles/responsibilites 1:1 in automation platform (e.g. UiPath Orchestrator) | Certain applications should only be accessed with specific production credentials (e.g. Epic PRD) on production machines External applications/extensions need to go through a security clearance process so it's important to use internal software when available (e.g. Microsoft Authenticator instead of Google Authenticator extension) | Not Started
Other | Upgrades | IT shares an upgrade schedule/release notes for anything that may impact the automation | Rebuild after upgrade go-live date, automation will be down for a period of time depending on scale of upgrade |  | Not Started
| Scheduling | Each automation requires a trigger, whether it's a certain time of day or an event trigger, for every run | Manual kickoff of automation is not efficient and trackable | Depending on access, IT may need to work closely with the developer to set up triggers for automations | Not Started
| SLAs | Determine the SLA for the automation program. If following the standard IT SLAs, ensure the team is aware of the expectations and incorporates them into program timelines | Automation development/maintenance delays | 5-10 days for new infrustructure requests (not break-fixes) for machines, credentials, etc. Anything dealing with patient care or impacting a production automation will be finished faster. 3-4 weeks for new machine templates or AD groups. | Not Started
| Ticketing | Requests are incorporated into the ticketing system and should be followed up on during a recurring meeting (e.g. Governance). All requests should be in one ticket if possible. | Multiple tickets for different requests is an inefficient use of everyone's time and will greatly delay completion of requests | Verify ticket requests via a meeting/phone call and complete all aspects of the ticket at the same time if able | Not Started