## Roles & Responsibilities
Tarpon Health
Automation Program Role | Key Responsibilities | Dedicated or Supporting?
Executive Sponsor | * Supports major program decisions and milestones: platform selection, hiring, project approval, etc. * Prioritization and input on the automation roadmap * Provides alignment with the broader organization | Supporting
Program Manager | * Leads and manages the automation program initiatives and results * Manages the RPA developers, SA, and supporting roles (e.g., report writer) * Leads the automation vendor / platform selection and maintains ongoing relationships * Facilitates the automation program governance committee and ensure all automation initiatives adhere to the automation governance model | Dedicated
Solutions Architect / Business Analyst | Performs: * Use case identification * Shadowing * Process mapping * Automation / solution design * Creating Process Definition Documents (PDDs) * Automation build and testing management * Identifies process improvement opportunities (unrelated to automation) | Dedicated
Automation developer | * Assists in the automation design, architecture, and documentation (e.g., PDD, SDD) * Builds automation solutions (RPA, APIs, etc.) * Tests automation solutions thoroughly * Makes updates to the automations throughout all phases (e.g., Build, Test, Maintenance) | Dedicated
Revenue Cycle operations / Business Process Owner | * Representatives from revenue cycle operations (i.e., VP, front, middle, back, etc.) * Identifies automation use cases * Aids in automation design and testing * Signs off on process map * Validates exports | Supporting
IT sponsor | * Establishes infrastructure * Integrating automations into the EHR * Insight into EHR roadmap / upgrade schedule * Programmatic data standardization | Supporting
Report writer | * Generates exports for bot processes * Creates workqueue adjustments | Supporting
Process improvement liaison | * Provides insight on revenue cycle process improvement projects including workflow and EHR optimization efforts to aid in RPA use case identification | Supporting
Compliance liaison | * Provides input/approval on compliance considerations | Supporting
Finance liaison | * Serves as the representative from finance for program budgeting and approval along with reporting out on automation ROI | Supporting

## Expanded Responsibilities
Tarpon Health
Automation Program Role | Detailed Responsibility List
Program Manager | * Facilitates the automation program governance committee and ensure all automation initiatives adhere to the automation governance model * Leads and manages the automation program initiatives and results, including the implementation of all automation solutions * Creates project plans, staffing plans, finanical plans, budgets, and status reports * Manages and coordinates across the automation team (Solution Architects, RPA developers, Operation Teams, IT, Report Writers, etc. * Manages issues, risks, changes, and escalations in the project * Manages application access and credentials for the automation team and the automation solution * Oversees the creation and maintenance of all project documentation * Obtains approval for project documentation * Assesses delivery readiness (e.g., is process improvement needed prior to build and is the automation performing accurately enough for go-live?) * Sets up and manages all operational meetings * Coordinates, forecasts, and documents enhancement and break-fix requests * Maintains the program charter * Hosts After-Action-Reviews and builds a culture of continuous improvement
Solutions Architect / Business Analyst | * Is knowledgeable of the business processes that will be automated based on the program's goals * Is knowledgeable of process improvement frameworks and methodologies * Identifies process improvement opportunities (unrelated to automation) * Works with operational stakeholders and organizational data to identify automation opportunities * Shadows operational teams to gather process requirements * Determines the automation solutions expected return on investement (ROI) * Process maps the current state process and the future state process (e.g. steps the automation will take) * Makes build reccomendations based on the finanical viability, complexity, and feasibility * Designs the automation solution, including the data inputs, data queuing, process steps (at the keystroke level), data logging, business exceptions, process exceptions, and expected outputs * Defines the architecture of the automation solution, such as technologies used, development techniques, integration / connectivity approach, and post-automation reporting * Creates the Process Definition Documents (PDDs) and Solution Design Documents (SDDs) * Creates a testing plan * Manages automation build, testing, go-live * Ensures the automation results are in-line with the approved design and requirements * Defines the automation dashboard requirements to measure the automation health and reconciliation with expected return on investement (ROI) * Scopes maintenance, enhancements, and break-fix changes across all automations
Automation developer | * Is knowledgeable of automation development techniques and best practices * Is knowledgable to the automation platform infrastructure, integration needs, access, and functionality * Assists in the automation design, architecture, and documentation (e.g., PDD, SDD) * Participates in operational / design meetings as needed * Builds automation solutions (RPA, APIs, etc.) that adhere to automation best practices and to business requirements * Tests all automations thoroughly * Makes updates to the automations throughout all phases (e.g., Build, Test, Maintenance) * Communicates updates to the automation team * Maintains all code repositories and objects * Builds additional technologies such as OCR, LLMs, Machine Learning, etc.