## Read Me First
Tarpon Health Sprint Planning Toolkit
Intended use
The intent of the Sprint Planning Toolkit is to provide a basic sprint planning template for development teams. Tracking progress granularly keeps teams on-track and within budget.
Why Sprints?
Definition: A sprint is a fixed-length period of time (typically 1-4 weeks) during which a team works on a specific set of tasks to achieve a specific goal. Sprints are often used in Agile software development, but they can also be used in other types of projects, such as RPA. Benefits: - Focus and productivity: Sprints force teams to focus on a specific set of tasks for a limited period of time. This can help to improve productivity and reduce distractions. - Early feedback and iteration: Sprints allow teams to get feedback on their work early and often. This can help to identify and fix problems early on, before they become too costly or difficult to address. - Agility and adaptability: Sprints allow teams to be more agile and adaptable to change. If new requirements or priorities emerge, teams can adjust their sprint plans accordingly.
Planning a Sprint
1.) The RPA manager / lead developer presents the sprint goals (based on business needs). 2.) The team discusses the sprint backlog and identifies the work that is needed to achieve the sprint goal. 3.) The team estimates the time required to complete each piece of work. 4.) The team prioritizes the work and selects the work that will be completed in the sprint. 5.) The team updates the sprint backlog. 6.) The work gets built into a tool to track the progress.

## Sprint Planning Template
Tarpon Health Sprint Planning Toolkit
Sprint Planning Template
Intent: Use this section to plan your sprints. Directions: 1. Prior to beggining your sprint, enter the goals, start date, and end date 2. Complete out each line with the task and associated details that you plan 3. Make a copy of the table (or tab) and repeat for Sprints 2+
Sprint 1
ENTER Goals ENTER Start Date ENTER End Date
Task Name | Task Category | Owner | Start Date | Anticipated End Date | At Risk? | Risk Reason | Actual End Date | Expected Hours | Actual Hours | Status | Next Steps / Comments
Not Started
Sprint 2
ENTER Goals ENTER Start Date ENTER End Date
Task Name | Task Category | Owner | Start Date | Anticipated End Date | At Risk? | Risk Reason | Actual End Date | Expected Hours | Actual Hours | Status | Next Steps / Comments
Not Started

## Sprint Backlog Template
Tarpon Health Sprint Planning Toolkit
Sprint Backlog Template
Intent: Use this section to capture your sprint backlog items Directions: 1. Place tasks and their associated details to this tab if they are deprioritized or discovered as you move through your current sprint. 2. Complete out each line with the task and associated details that you plan 3. Prior to beggining your next sprint, review and move tasks from this section into your current sprint
Sprint Backlog
Sprint Number | Task Name | Task Category | Owner | Start Date | Anticipated End Date | At Risk? | Risk Reason | Actual End Date | Expected Hours | Actual Hours | Status | Next Steps / Comments

## Data Validation
Task Category | At Risk? | Status
IT / Infrastructure | Yes | Not Started
Access | No | In Progress
Design |  | Needs Review
Development |  | Overdue
Testing |  | Completed
Go-Live
Post Production
Other

## Drop Down Selections (hidden)
Desired Bot Process | Process Schedule & Frequency | Input Lists | RPA Platform Used | Designation | Systems | System access | Owning Area
Adjustments | Daily | Epic Export | UiPath Studio | HB | Epic | Citrix | Referral MGMT | y
Secondary Billing | Weekly | Analytics Tool Export | UiPath Studio X | PB | Cerner | VDI (Virtual Desktop Infrastructure) | Scheduling | Yes
Transfer balance (NRP) | Monthly | Third Party Export | Automation Anywhere | Other | Soarian | Other | Pre-Reg & Financial Clearance | No
Coordination of Benefits | Other | Direct Application, no queue | Blue Prism |  | STAR |  | POS collections | Unknown
Claim Edits |  |  | Pega |  | Meditech |  | Financial Counseling
Claim Status |  |  | Other |  | AllScripts |  | Care Management
Authorization Status |  |  |  |  | Quadax |  | Charging
Owning Area Transfer (Epic) |  |  |  |  | Claim MD |  | HIM
Eligibility Status |  |  |  |  | Waystar |  | Coding
Balance Consolidation |  |  |  |  | Apex EDI |  | Revenue Integrity
Medical Records |  |  |  |  | Emdeon |  | Contract Management
Note Posting |  |  |  |  | Availity |  | Billing
Portal Exports/Portal Uploads |  |  |  |  | RelayHealth |  | Follow-up
PAS Record updating (Auth) |  |  |  |  | Other |  | Cash Posting
Other | [6 empty] | Self-pay Management
Credits